## Slide 1: CSPS Technology Integration Projects Business Case
Stephen Dwnes
March 24, 2017
National Research Council Canada
Conseil national
de recherches Canada

## Slide 2: Overview
Integrated set of proposed activities:
  performance support and resource recommendation services
  an expansion of events and subscription-based learning
  pilot collaborative rapid resource authoring and curation
  integration of programs and services with other government platforms
Duration of 3 years (outcomes for an additional 3 years)
  staffing is between 12.5 and 15.5 FTE
  $4.41 million over three years
  IT staff, instructional designers, program development staff, needs analysis and assessment.

## Slide 3: The Challenge
Evolving model of online learning support
  from classes to mobile support, personalization and crowd-sourcing
  example: Accenture Connected Learning
Expansion of GoC intranet support
  Gctools (GCconnect, GCcollab, GCpedia, etc.)
Requirement to follow-up development of GCcampus
  CSPS identified five areas for program
  mobile, personalization, integration with GCtools, crowdsourcing and virtual library.

## Slide 4: Analysis
CSPS has made significant progress extending its platform beyond the LMS (to include Drupal, Moodle, Kaltura)
The school’s structural and service orientation has not aligned to new technologies and pedagogies.
Analyst Recommendations:
  define and align to a contemporary model of online learning support
  conduct an incremental, rather than a rapid expansion of any individual service

## Slide 5: Contemporary model of learning support
Need for staff and learners to work with and understand new learning pedagogies as part of the process of developing a consensus
Need to reassess its development cycle and model in order to support rapidly changing needs
Needs to integrate a process of continuous needs generation and performance assessment into learning program development and delivery.

## Slide 6: Incremental rather than a rapid expansion
The school has not yet had time to implement the new functionality that has already been installed
Changes in the wider learning technology infrastructure environment will impact GCcampus
Need to develop experience and skills in performance support as well as course-based learning
No single one of the services (mobile, personalization, crowdsourcing, library, integration) can be expanded without impacting the remaining four.

## Slide 7: Strategy
Speak to the role of the School not merely as a provider of learning and learning resources, but also to its role in developing a learning culture in the public service
Define and align to a contemporary model of online learning support
Develop solutions incrementally rather than a rapid expansion of any individual service
Individual projects follow, in order of priority

## Slide 8
Mandate
Provide a broad range of learning opportunities and establish a culture of learning within the public service
Augmented online social presence
Key learning needs identified
Increased effectiveness of support
Integrate services in GoC functions
Continuous improvement
Benefits
CSPS resources in GCTools
Social & community pedagogies
Mobile end-user applications
Performance support function
Content recommendations
Pilot user blog, ratings, recommends
Personalized subscription services
Personal user learning dashboard
Events and podcasts
Rapid resource creation
Single signon
Risk assessments
Outcomes
Crowd-sourcing
Personal-ization
Mobile Platform
GC Campus Integration
Virtual Library
Projects
Priority
2
1
4
3
5
Content brokering

## Slide 9: Personalization
Texisting resource base does not support personalization based on adaptive systems
The future LMS environment (if any) must be defined
Concrete steps can be taken to prepare staff and students
  Content recommendations from GoC libraries
  Personalized subscription-based services
  User learning dashboard with metrics

## Slide 10: Crowdsourcing
Depends on the ability and willingness to integrate learner and third party feedback and contributions
Necessary to develop the school’s capacity and comfort level with crowdsourcing
  Learning and development pedagogy review and pilot process
  Pilot user blog, ratings or recommendations
  Risk assessment for accessibility, privacy, security

## Slide 11: Integration with other government services
Primary target for integration is GCTools
Desirable to integrate with human resources, competency and performance management systems
All integration requires c oordination with external services, some of which are not yet fully developed
  Integration with single signon services – this was single most-requested feature was single-signon
  CSPS resources launched from GCTools, GoC dashboards

## Slide 12: Mobile
Mobile devices are not suited to the delivery of online courses
Not practical to develop platform-specific apps (eg. iPhone app).
  Mobile support in this context should focus on responsive and cross-platform design (for example, HTML5-based design)
‘Mobile learning’ entails support for learner mobility,
  Support for specific end-user applications
    Includes elements of GCcampus website
    Includes learning resources
    Support for crowdsourcing
  Events and podcasts in audio/video viewers

## Slide 13: Virtual Library
Desirable to provide access to eBooks to support online courses
Not desirable to duplicate library services are being offered in various departments
Purpose of a CSPS virtual library is to support performance support
More than just eBooks; learners require access to videos, podcasts, learning objects
  Standardized performance support function
  Collaborative rapid resource authoring
  Content brokering from GoC and partner libraries

## Slide 14: Benefits
Identify and deliver key learning and performance support needs
1
Augmented online social presence
2
Integrated CSPS services with those of other departments and functions
3
Increased effectiveness of learning and performance support
4
Continuous improvement in learning technology
5

## Slide 16: Resources

## Slide 17: Risks

## Slide 18: Project Team
Stephen Downes – principle investigator
Bruno Emond – project lead
Hélène Fournier – research officer
Irina Kondratova – research officer
Shirley MacLeod – knowledge management
 | National Research Council Canada | Conseil national de recherches Canada